Midwest City Community Members

Midwest City Comp Plan Project Team

Monthly Project Update: May 2025

TO

FROM

SUBJECT

Dear Midwest City Community Members,

We are pleased to provide you with the latest updates for the month of April regarding the Midwest City Comprehensive Plan 2045: A Plan for the Future. Our team has been actively engaging with the community and progressing with key components of the plan. Below are the latest highlights:

Recent Activities:

- Earth Day Festival (April 26): The event saw a strong community turnout, where we gathered valuable feedback on the Future Land Use scenario preferences and priorities for public fund allocations. For those unable to attend, a survey is now available on the project website to provide input and share your vision for Midwest City’s future development.

- Student Survey Development: Student surveys have been developed, which will be distributed to students in the Mid-Del school district and Rose State College. This initiative aims to capture youth and young adult perspectives on the future growth and development of Midwest City.

- Plan Development and Public Engagement Analysis: The planning team continues to draft the Community Snapshot, Vision and Guiding Principles, and Future Land Use chapters, incorporating community feedback and ongoing data analysis.

- A draft market analysis is being reviewed and finalized to support plan recommendations and offer greater insight into the City’s economic development opportunities and challenges.

Upcoming Tasks:

- Steering Committee Meeting (May 20): The project team will meet with the Steering Committee to review progress, discuss community feedback, and refine strategies for the upcoming phases of the Comprehensive Plan.

We greatly appreciate your continued participation and support. Your input remains invaluable in shaping a plan that aligns with the community’s needs and aspirations. Please stay connected for further updates and additional opportunities to get involved through our project website.

Project website: https://fni.mysocialpinpoint.com/midwest-city-comprehensive-plan