Midwest City Community Members

Midwest City Comp Plan Project Team

Monthly Project Update: September 2025

TO

FROM

SUBJECT

Dear Midwest City Community Members,

We are pleased to share the latest progress made during the month of August for the Midwest City Comprehensive Plan 2045: A Plan for the Future. Our team continues to work closely with City staff, technical partners, and the Steering Committee to advance the plan’s development.

Recent Activities:

- Draft Chapter Distribution: Draft chapters for Community Snapshot, Vision and Guiding Principles, Land Use and Development, Housing, Community Character and Urban Design, and Economic Resiliency were distributed to City staff, technical stakeholders, and the Steering Committee for review.

- Steering Committee Meeting #4 (August 18): The Steering Committee met to review the completed plan elements and begin identifying potential action items for each chapter, ensuring that future strategies align with the plan’s goals.

- Follow-Up Survey: A survey was sent to the Steering Committee following the meeting to collect additional comments, suggested revisions, and ideas for action items. The survey remains open, and responses will be used to inform final edits and implementation strategies.

- Meeting with EMBARK (August 21): The planning team met with EMBARK, the regional transit agency, to discuss the future of transit services in Midwest City. This conversation provided valuable direction for continued development of the Transportation chapter.

Looking Ahead:

- Finalizing Draft Chapters: The team is working to finalize drafts of the Transportation and Public Facilities and Infrastructure chapters for internal and committee review.

- Developing the Implementation Chapter: Work is also beginning on the Implementation element of the Plan, which will outline a set of key action items to guide the City in achieving its long-term goals.

- Steering Committee Meeting #5: The final Steering Committee meeting (date to be determined) will focus on reviewing the full draft of the Comprehensive Plan and discussing implementation strategies and action items across all chapters.

Thank you for your continued support and engagement. Your feedback plays a vital role in helping shape a plan that reflects the shared values and vision of Midwest City.

Project website: https://fni.mysocialpinpoint.com/midwest-city-comprehensive-plan