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Dear Midwest City Community Members,

We are pleased to share an update on the progress of the Midwest City Comprehensive Plan 2045: A Plan for the Future. Over the past month, significant efforts have been made to gather community input and advance the planning process. Below are key highlights of our recent work. 

Recent Activities:
· Stakeholder Interviews: The Planning Team has been conducting interviews with key stakeholders to gather insights specific to various groups throughout the community. 
· Public Engagement Analysis: The Planning Team has been reviewing feedback collected from both the public (1/14/25) and virtual open house (available from 1/14/25 to 2/15/25).
· Steering Committee Visioning Exercise: The project’s Steering Committee met on 2/21/25 to engage in a visioning exercise, helping to shape the long-term direction of the plan. 
· Formulation of Guiding Principles: Guiding Principles for the plan were developed based on community input and analysis. 
· Ongoing Coordination: Staff and the FNI team continue to meet regularly to discuss project progress and key topics.

Upcoming Tasks: 
· Development of Plan Chapters: Work will begin on drafting the Community Snapshot, Vision, and Guiding Principles chapter of the Plan. 
· Market Analysis: A market analysis will be finalized to inform and support plan recommendations relating to economic development, housing and land use. 
· Earth Day Festival Community Engagement: We will have a presence at the upcoming Earth Day festival to engage with the public and gather additional input related to Future Land Use and Transportation. 
· Student Survey: A student survey is being developed, with planned outreach to students in the Mid-Del district and at Rose State, to capture youth perspectives on the future of Midwest City. 
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AI-generated content may be incorrect.]We greatly appreciate your ongoing participation and support in this process. Your input is invaluable in shaping a plan that reflects the needs and aspirations of Midwest City. Please view the project website for further updates and additional opportunities to get involved. 
Project website: https://fni.mysocialpinpoint.com/midwest-city-comprehensive-plan
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