Midwest City Community Members

Midwest City Comp Plan Project Team

Monthly Project Update: August 2025

TO

FROM

SUBJECT

Dear Midwest City Community Members,

We are pleased to share the latest updates on the Midwest City Comprehensive Plan 2045: A Plan for the Future. Throughout July, our team continued to advance key aspects of the plan in close coordination with City staff.

Recent Activities:

- Chapter Development and Staff Review: Drafts of the Community Snapshot, Vision and Guiding Principles, Future Land Use, Housing, and Community Character and Urban Design chapters have been completed and sent to City staff for review. Feedback from this review will help shape the next round of refinements.

- Steering Committee Meeting Scheduled (August 18): The next Steering Committee meeting is scheduled for August 18. The committee will review the initial draft chapters to check for responsiveness to community input and provide guidance on next steps.

- Coordination with EMBARK: A meeting with EMBARK, Oklahoma City’s regional transit agency, has been scheduled to inform the Transportation chapter and ensure alignment with regional mobility efforts.

- Next Group of Plan Chapters: Work is well underway on the next set of chapters: Transportation, Infrastructure, and Implementation, which are nearing completion. These chapters will complete the core content of the Comprehensive Plan.

Looking Ahead:

- Upcoming Steering Committee Meeting (Late September/Early October): A subsequent Steering Committee meeting is being planned for late September or early October to review the full draft of the Comprehensive Plan and discuss the Implementation chapter in detail.

- Ongoing Coordination: The planning team continues to meet regularly with City staff to align priorities and refine content across the full suite of plan chapters.

Thank you for your continued engagement in the planning process. Your input plays a critical role in creating a roadmap that reflects the community's vision and aspirations. Please stay connected through our project website for updates and opportunities to participate.

Project website: https://fni.mysocialpinpoint.com/midwest-city-comprehensive-plan