Midwest City Community Members

Midwest City Comp Plan Project Team

Monthly Project Update: November 2025

TO

FROM

SUBJECT

Dear Midwest City Community Members,

We are pleased to share the latest updates from October for the Midwest City Comprehensive Plan 2045: A Plan for the Future. The project continues to move forward with final edits and key milestones as we near plan adoption.

Recent Activities:

- Ongoing Draft Edits: The project team continued to revise plan chapters to incorporate feedback received from City staff. These updates ensure that the plan reflects local priorities and addresses technical considerations.

- Steering Committee Meeting #5 (October 30): The final Steering Committee meeting was held to review and discuss the draft implementation chapter, focusing on action items and their prioritization. Committee input during this meeting will help shape the final strategies and timeline for implementation.

- Ongoing Staff Coordination: Regular meetings with City staff have supported continued alignment on revisions and preparation for upcoming public engagement and approval milestones.

Looking Ahead:

- Final Open House (November 18): Community members are invited to review the full draft of the Comprehensive Plan and the implementation framework during the final open house. This is an opportunity to learn about the plan and ask questions before the formal adoption process begins.

- Planning Commission Meeting (December 2): The Planning Commission will review the final draft and consider a recommendation for adoption.

- City Council Hearing (January): The City Council will hold a public hearing to review and consider adoption of the final Comprehensive Plan.

Project website: https://fni.mysocialpinpoint.com/midwest-city-comprehensive-plan

We are grateful for your continued engagement as we approach the final steps in this important planning process. Your feedback and involvement have been vital in shaping a plan that reflects the vision and needs of Midwest City.