Midwest City Community Members

Midwest City Comp Plan Project Team

Monthly Project Update: April 2025

TO

FROM

SUBJECT

Dear Midwest City Community Members,

We are pleased to provide a recap of the progress made in March for the Midwest City Comprehensive Plan 2045: A Plan for the Future. Our team has been actively engaging with the community and advancing key components of the plan. Below are the latest updates:

Recent Activities:

- Neighborhood Outreach: Staff has been making rounds to neighborhood groups to encourage their involvement in the planning process and ensure community voices are heard. This effort is ongoing.

- Plan Development: The planning team is actively drafting the plan's Community Snapshot, Vision, and Guiding Principles Chapter and the Future Land Use Chapter.

- Public Engagement Analysis: Continued review and incorporation of community feedback into the planning process.

- Ongoing Coordination: Staff and the FNI team continue to meet regularly to discuss project progress and key topics.

Upcoming Tasks:

- Earth Day Festival Community Engagement: We will have a presence at the upcoming Earth Day festival (April 26)  to engage with the public and gather additional input related to Future Land Use and Transportation.

- Student Survey: A student survey is being developed, with planned outreach to students in the Mid-Del district and at Rose State, to capture youth perspectives on the future of Midwest City.

We appreciate your continued participation and support. Your input remains invaluable in shaping a plan that reflects the needs and aspirations of our community. Please stay connected for further updates and additional opportunities to get involved.

Project website: https://fni.mysocialpinpoint.com/midwest-city-comprehensive-plan